## General Tasks
| Mon 10/10/22 - Sun 10/16/22 | Mon 10/17/22 - Sun 10/23/22 | Mon 10/24/22 - Sun 10/30/22 | Mon 10/31/22 - Sun 11/06/22 | Mon 11/07/22 - Sun 11/13/22 | Mon 11/14/22 - Sun 11/20/22 | Mon 11/21/22 - Sun 11/27/22 | Mon 11/28/22 - Sun 12/04/22 | Mon 12/05/22 - Sun 12/11/22
| Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Team Timeline | Week 8: Field Research
Theoretical Design
Physical Design (Implementation)
Application (Testing)
** user research plan - otter user
** object interaction (natural/aquarium), sensors in one of those

## Individual Tasks
| Mon 10/10/22 - Sun 10/16/22 | Mon 10/17/22 - Sun 10/23/22 | Mon 10/24/22 - Sun 10/30/22 | Mon 10/31/22 - Sun 11/06/22 | Mon 11/07/22 - Sun 11/13/22 | Mon 11/14/22 - Sun 11/20/22 | Mon 11/21/22 - Sun 11/27/22 | Mon 11/28/22 - Sun 12/04/22 | Mon 12/05/22 - Sun 12/11/22
| Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Team Timeline | Week 8: Field Research
Theoretical Design
Physical Design (Implementation)
Application (Testing)
Nathaly | Week 8: Lead otter toy interaction research; Week 10: Assist with physical toy development; Week 13: Iterative Revision Based on Data Analysis & Additional Research; Week 16: Project Presentation & Demo
Dhruv | Week 8: General otter toy interaction research; Week 10: Lead physical toy development; Week 13: Iterative Revision of Physical Device
Adithya | Week 8: General otter toy interaction research; Week 10: Lead physical toy development; Week 13: Iterative Revision of Physical Device
Jacqueline | Week 8: Develop User Research Plan with Otter as User; Week 11: Integration with Physical Project Status; Week 13: Interative Revision
Notices | Week 8: 20th: Project Plan Due; Week 10: 26th: Midterm Due; Week 12: 7th: Progress Report Due; Week 15: 4th: Final; Week 16: 6th/15th: Final Presentations
20th: Team Contract Due
* Fall Break (Mon, Tues)